## Introduction
INTRODUCTION
Scope
The S-APQP and PPAP template is the reference used to configure the Supplier Quality Project in the Veoneer PLM system accessed by supplier via the VPP.
It is covering both S-APQP AND PPAP activities and deliverables avoiding work done in parallel because of both requirements.
Use of template
The supplier shall use this template as a guideline to remind activities to be carried out in relation to each task he will have to carry out.
This template shall not be used to report status on S-APQP and PPAP activity.
The supplier shall instead use the Supplier Quality project (SQP) IT VPP application to document and upload all deliverables in relation with the tasks and activity listed.
Rules for documentation and submission of deliverables
As currently in both PPAP and S-APQP, task will not require mandatory documentation and submission by the supplier.
Documentation and submission in SQP application will depend on the PPAP level submission and Control Level Definition agreed upon with Veoneer authority.
Definition of CLD and PPAP submission level will automatically configure the scope of S-APQP and PPAP to be documented.
CLD definition will automatically configure tasks that does not require a formal submission, validation and review in time as currently allowed in VSM.
Activity Planning
Planning of activities is carried out by Veoneer Project SQ. Supplier is allowed through the SQP IT application in VPP to propose new timing to Veoneer SQ on some activities.
Change will be applied after approval by the Veoneer SQ.

## S-APQP tasks
Supplier Quality Project Task | Deliverable Description for SQP | Feature APQP/ PPAP | Reference Requirement # in AIAG PPAP Manual | PPAP Level | APQP Requirement
Feasibility Study |  | APQP |  | 1 | The supplier project team shall perform a feasibility study to verify that all technical data, qualities and functions are correctly stated and that it is possible to achieve them. The supplier reports the results by using the Team Feasibility Commitment template (TFC-template). Any open items must be closed before the activity "Feasibility Study" is defined as completed and PSW is submitted.
Design FMEA | Upload DFMEA (if you do not have design authority, upload 1 page that states "Not applicable for this part number" | PPAP | 4 | 3 | DFMEA's shall be done according to the guidelines in the AIAG Failure Mode and Effects Analysis handbook. If the supplier is not Design responsible, the DFMEA is completed by Veoneer. All pertinent information from the D-FMEA shall be communicated, understood and agreed upon between supplier and Veoneer to ensure full consistency between the D-FMEA and the P-FMEA. The supplier is responsible to assure that all necessary D-FMEA information is received in order to develop the P-FMEA. (See also item 15. P- FMEA below). If the supplier is responsible for the design, a D-FMEA shall be completed and submitted to Veoneer together with an action plan for acceptance by Veoneer. For semiconductors and electronic components submission of pin DFMEA, indentifying potential failure modes on pins and FTA (Fault tree analysis), showing the potential combinations of basic events leading to an undesirable event, are required. FTA study must be in accordance with the international standard IEC 61025.D-FMEA shall be planned so that necessary actions can be implemented before the design phase of the project is closed. (Ref. VS104 D-FMEA (Potential Failure Mode and Effects Analysis in Design))
Substance Review | Upload Approved Waiver Request Form for Forbidden Substances. (Ref VSM:VS5 Veoneer Specification) If this is not applicable, upload 1 page that states "No forbidden substances used in the production of this component" | PPAP | 17 | 3 | The supplier shall, independent of whether Veoneer or the supplier makes the material selection, review the composition of each material. In the case of supplier designed or chosen materials, the supplier shall make sure the defined material conforms to the VS005. Materials, components and products containing substances classified as forbidden must not be used. If needed due to safety or other requirements, and no other alternatives exist the supplier shall notify Veoneer immediately, which will initiate a deviation process. Any deviation must ultimately be acknowledged by the vehicle manufacturer and approved centrally by Veoneer to become effective. (Ref. VS005)
Contract Review | Upload agreed and signed Contract Review (Veoneer Document provided by Project Buyer) | APQP |  | 3 | This review is held with the appropriate participation from Veoneer and the supplier. The aim is to review and confirm all aspects in the contract between Veoneer and the supplier ( i.e. technical, commercial, logistic, quality , timing, results from the feasibility study etc.) The template "Contract Review" shall be used to document the agreements.
Key Milestone 1: Phase 1 | APQP Review confirmation. To be promoted by Veoneer SQ after review and release of all tasks related to this Milestone. | APQP |  | 3 | Milestone 1 aims at checking that all activities planned during Phase 1 are completed and that project can proceed.
Special Characteristics | Upload the completed CC/SC list and Measurement Agreement Sheet (Ref: VSM - VS052) | PPAP | 11,17 | 3 | The process to identify, control and verify Special Characteristics during development, PPAP and serial production shall be performed according to VS052. The CC/SC's shall be documented in the CC/SC list (VS052 ). All identified CC/SC's carried through to all relevant documents (i.e. drawings , control plan, work instructions etc.). If Veoneer is responsible for the design, the supplier shall receive information about CC/SC's from Veoneer. The supplier shall as a result from his P-FMEA process create a CC/SC list including the CC/SC's identified by Veoneer and by the supplier. The results from this process shall also be used to define those characteristics or process parameters which shall be controlled by SPC, 100% detection of defects, Poke-Yoke or other method agreed to by Veoneer during serial production. The supplier shall submit results from his ongoing control and verification of CC/SC's as directed by the using Veoneer facility. Further, if nothing else is specified, the below mentioned characteristics must be verified on finished components after all manufacturing process steps have been completed, prior to shipping of a manufacturing lot/batch to Veoneer. Method of testing to be agreed with Veoneer. The verification shall be included in the Control Plan.
Lot Traceability Plan | Upload Lot Traceability Flowchart. (Ref: VSM - VS4) | PPAP | 5 | 3 | The supplier has to establish a plan to define how all raw material, components, sub-components, and production processes are traceable to the manufacturing lot/batch number or individual serial number. The requirements also apply as appropriate to any sub-contractor. (Lot/batch size is defined in VSM-Quality Requirements -"General")
Process Flow chart | Upload Process Flowchart that includes all process steps, inspections and tests including stock and transport activities. (Ref: VSM - PPAP requirements) | PPAP | 5 | 3 | The production process shall be planned and reported on a flow chart (including a lay-out) where all supplier, sub-supplier and transportation operations / processes are described. All operations shall be marked and correspond to P-FMEA and Control plan The Process Flow Diagram shall include all processes from receiving, handling, manufacturing, final inspection, final product audit and dock-audit.
Process FMEA | Upload the Process Failure Mode and Effect Analysis including completed PFMEA Go & See Worksheet. (Ref: VSM - VS104 Appendix C Veoneer Standard) Note: P-FMEA must be clearly linked to the process flow chart and control plan. All CC/SC characterisitics shall be addressed. | PPAP | 6 | 3 | P-FMEA´s shall be done according to the guidelines in the AIAG Failure Mode and Effects Analysis handbook.P-FMEA shall be carried out on the basis of the input from the D-FMEA , after a production layout and a process flow chart have been produced. The P-FMEA analysis performed by the supplier shall be reviewed with Veoneer to ensure that the D-FMEA and the P-FMEA are consistent including CC/SC's, failure effect , severity ratings, etc. Knowledge of the product, production and inspection equipment capability shall always be considered. (Ref. VS104). Suppliers should refer to Veoneer Commodity Specific Master PFMEA to assure that all noted failure modes have been addressed in their specific PFMEA. Questions to assist completeness: - Is the right part number and current index referred? - Have top severity issues been addressed with recommended actions? - Are adequate controls in place for all CC/SC characteristics? - Has "Go&See PFMEA" (GS&F) using the GS&F PFMEA Checklist been performed? - Have all documents been updated as applicable and all GS&F findings closed?
Supplier Timing Plan | Upload complete time plan including procurement of Production Tooling and Measurement Equipment. | APQP |  | 2 | A plan (incl. timing) shall be established for production tools and product specific control instruments. The plan must include timing regarding preparation of tooling drawings/specifications, manufacturing and qualification of the tooling. Identified and defined tools and production equipment that shall be used for serial manufacturing shall be available at the time for the Production Trials and Product/Process Validation. Furthermore the main trial runs, FOT part availability and other dates required by Veoneer shall be included.
Qualified Laboratory Documentation | Upload all laboratory accrediations and scopes including raw material; i.e. ISO 17025, TS 16949. Must be current. | PPAP | 12 | 2 | The supplier shall provide evidence that if he is planning to use an external laboratory for some measurement, this laboratory is certified by national certification body for the service provided.
Sub-Supplier PPAP | Upload signed PSWs from ALL sub-suppliers. | PPAP | 10 | 2 | The material or components that shall be used must have APQP and PPAP activities planned. These must show that the materials are approved within the timeframe of the project and that used sub suppliers were selected according to defined supplier requirements. Even if the sub supplier is selected by Veoneer, the supplier is responsible for sub supplier APQP and performance. The supplier shall ensure that all components and materials to be used for serial manufacturing are PPAP approved or certified to raw material specification. Only approved material shall be used for manufacturing of PPAP parts and for product/process validation.
Special Processes | Upload Applicable Assessment Report. (Ref: VSM - VS69) | PPAP | 17 | 3 | Special processes are processes where following inspection and testing cannot totally verify the results. Examples are: heat treatment, welding, surface treatment, gluing, soldering etc. Special processes shall be controlled and documented to assure the output meets specifications. All required fixed parameters are to be defined as process instructions in the control plan. For special processes, acceptable results from an audit as defined by VS069 is required before PPAP can be approved. (Ref. VS069 "Special Processes-Requirements and Assessments")
Material Handling and Packaging Instructions | Upload approved packaging form and copy of shipping label. (Ref: VSM - Logistics Requirements - Section: Packaging and section: Labeling VS244) | PPAP | 17 | 3 | The supplier shall complete an analysis of all handling and labeling which the product is subject to (from delivery of raw materials, through manufacturing to delivery to Veoneer) with the aim of ensuring that the materials/products are identified, handled, stored, packed and transported in such a manner that a change or deterioration is prevented. A plan for material handling shall include the product flow, replenishment system, and packaging (Ref. VSM Logistics Requirements)
Engineering Sample Approval | If applicable, upload approval & comments from sample evaluations. | APQP |  | 2 | If samples are evaluated by Veoneer e.g. form, fit and/or function, the approval and comments shall be documented. Samples shall be delivered to Veoneer for approval (Ref. AIAG PPAP Manual)
Appearance Approval Reports | Upload approved AAR Forms. (Ref: VSM; AIAG Manual-PPAP) | PPAP | 13 | 1 | The supplier shall plan for evaluation of parts with visible surfaces, structure and colour. Samples and measuring results shall be reported on AAR and submitted to Veoneer for approval. ( Ref. AIAG PPAP Manual - AAR template) Note: AAR and representative production products shall be submitted to the location assigned by Veoneer to await disposition. AAR shall be submitted to Veoneer SQ in the final submission. This should include the appearance boundary sample as required by Veoneer SQ. Questions to assist completeness of AAR submission: - Is there a separate and complete AAR for each part / dash number? - Is the top section of the form filled out correctly and completely? - Is the "Appearance Evaluation" section filled out correctly and completely? - Is the "Color Evaluation" section filled out correctly and completely? - Does the supplier have Master Color/Grain samples at their manufacturing location? - Is the AAR signed by the production component supplier? - Is the AAR signed by the customer representative if required? If not, is there an action plan being lead by Veoneer Program Management?
Checking Aids | Upload photos of all checking aids and documentation/description of any specific gauges or fixtures appearing in Control Plan including acceptance criterial of attribute gauges. | PPAP | 16 | 3 | The supplier shall review and evaluate the defined measuring and test equipment (available and planned ) and its capacity. The activity includes specification, procurement and validation of measuring and test equipment to be used for manufacturing of the product. The supplier shall provide evidence that Checking Aids have been produced, documented and commissioned as efficient to check components. It is expected that supplier maintains the checking tools during the product lifecycle and does Measurement Systems Analysis (MSA) according to Veoneer’s requirements. Questions to assist completeness: - Are all checking aids included in the Control Plan? - Are all checking aids provided for with preventative maintenance plans? - Do all checking aids have acceptable MSA studies?
IMDS Approval | Upload screen shot of approved IMDS submission. Ref: VSM PPAP guidelines Section 1.1 IMDS Reporting Guidelines. | PPAP | 17 | 1 | The materials shall be declared by the supplier through IMDS, according to the requirements and guidelines defined by the VS005, and approved by Veoneer.
First Production Trial Run and Corrective Actions | Upload Production Trial Run Report, phase First Trial Run (Ref: VSM - Veoneer Production Trial Run Standard). | APQP |  | 2 | The supplier shall schedule the First Production Trial Run to ensure adequate time for corrective actions before the PPAP Production Trial Run. Requirements and documentation shall be as defined in " Production Trial Run Standard ". (Ref. VSM Product Life Cycle Step 7 "Production Trial Runs " and the " Production Trial Run Standard ".)
Key Milestone 2: Phase 2 | APQP Review confirmation. To be promoted by Veoneer SQ after review and release of all tasks related to this Milestone. | APQP |  | 2 | Milestone 2 aims at checking that all activities planned during Phase 2 are completed and that project can continue.
Dimensional Results | Upload Dimensional Results for five parts. Note: Include numbered (ballooned) drawing with results. (Ref: VSM PPAP requirements) | PPAP | 9 | 2 | The supplier shall provide the first dimensional results including preliminary capabilities after the First Production Trial Run. Dimensions with deviations shall be identified and IRW proposed only if supplier cannot make changes to get parts to requirements. Reports of all dimensions and parameters documented in the design records for all cavities and each unique manufacturing process is required. The dimensional report must be keyed to the design record (ballooned). The supplier shall respond to each drawing note and specification item. Blanket statements are not allowed. Test results and a "pass/fail" statement is required. Number of samples, unless otherwise agreed to, is five (5). For assembly part, if the dimension for sub-components are defined in Veoneer drawing and specification, the dimensional result shall include all dimensions for sub-components defined on Veoneer drawing and specification. Questions to assist completeness: - Is the right part number and current index referred to? - Are all CC/SC's highlighted? - Do results meet all drawing and note specifications? - Are any nonconformances highlighted in the report with an approved (IRW) by Veoneer? - Are layout results legible and understandable? - Are the dimension result sheets completed in English and signed?
PPAP Production Trial Run | Upload Production Trial Run Report phase PPAP (Ref: VSM Veoneer Production Trial Run Standard). | APQP |  | 2 | Date for PPAP Production Trial Run as well as the time required for PPAP preparation and submission shall be scheduled and included in S-APQP. (Ref. VSM Product Life Cycle Step 7 "PPAP and Run at Rate" and " Production Trial Run Standard "). Refer to VSPP CLD document for additional information as needed.
Measurement System | Upload all gage R&Rs on measurement equipment used for Initial Capability Studies and for acceptance of SC/CC characteristics as outlined in the Control Plan. (Ref: VSM - PPAP requirements; AIAG Manual - MSA) | PPAP | 8 | 3 | The supplier shall conduct an evaluation of all test and measuring methods that are planned for serial production. Gauge R&R values for measuring method, including operator, material and environmental variations shall be documented in the PPAP. Special attention shall be considered for verification of measuring method regarding CC / SC. (Reference: AIAG Manual "MSA Reference Manual") Questions to assist completeness: - Are MSA studies for all equipment (gages, measurement, test) used to accept product? Minimum is Type 2 GR&R. Other like type1, bias, linearity, stability studies if requested. Reference AIAG MSA manual. - Are MSAs for all variable CC/SCs available? - Does MSA refer to the correct part number and current index referred? - Are the used measurement devices clearly identified? For additional information, please refer to AIAG "Measurment Systems Analysis" reference manual for specific guidelines to follow.
Initial Capability Studies | Upload Initial Capability Studies. 100 parts in total required for all CC, SC. (Ref: VSM - PPAP requirements) | PPAP | 11 | 3 | The supplier shall provide a preliminary process capability study (Ppk) on all CC’s and SC's to identify and verify the manufacturing process capability. Default requirement is Ppk studies required on all CC’s and SC’s as indicated on Veoneer drawings and related specifications. Reports of capability studies are performed on defined process steps and product characteristics on greater than 100 parts from a continuous production run. For unstable processes, are corrective actions implemented and a modified Control Plan included in the PPAP submittal and 100% inspection in place and defined in the Control Plan. Processes to be controlled by statistical methods to be identified and reported in control plan. Special requirements applies for CC/SCs. Test results and a “pass / fail” statement is required. (Ref. "Production Trial Run Standard", VS052, AIAG Manual "PPAP and "SPC"). Questions to assist completeness: - Are all CC/SCs from the drawing (and drawing notes) included? - If not: is a measurement agreement for CC/SC dimensions attached? - Does the data indicate the process is under control (according to VS052)? - Do the results refer to the correct part number and index? - Is the measurement method/device noted? - Are results for standard deviation and the distribution noted? - Is the sample size according to the CC/SC-Agreement or according to VS052? - Are all initial process studies completely in English? - Are statistical charts and data included? - If a CC/SC can't generate variables data, was the attribute data generated from a 300 piece run? - Does the attribute data indicate zero (0) defects were found? - Are controls in place to ensure CC/SC attribute characteristic will meet drawing requirements?
Material Certifications | Upload Material Test Results, Material and Performance Certifications and Product Validation Test Results. | PPAP | 10 | 2 | Validation plans for all material tests and performance qualifications shall be established and resources provided (equipment, personnel and laboratory) Veoneer will specify the qualification testing. If the supplier has the design responsibility, Design Validation shall be planned. Final product and process validation shall be realized by using serial status products. Questions to assist completeness: - Is a Material certificate available and does it refer to the right part number and index? - Do results meet all drawing and note specifications? - Are any nonconformances highlighted in the report and approved (Interim recovery worksheet) by Veoneer? - Are material test (chemical, metallurgical, etc.) results included? (See Appendix D AIAG PPAP Manual - Form CFG 1004) - Are performance test results included? (See Appendix E AIAG PPAP Manual - Form CFG 1005) - Has testing specification been identified on all tests? - Is the quantity tested identified (if required)?
Control Plan | Upload the production control plan. CP must be clearly linked to the process flow chart and PFMEA. It must include controls of SC/CC characteristics, Dock Audit and Annual Layout. (Ref: VSM - SQPS-412; PPAP requirements). | PPAP | 7 | 3 | The control plan shall be completed per the following AIAG APQP/Control Plan manual and IATF 16949. It shall be completed in three stages: Prototype, Pre-Launch (PV) and Production. It shall be created on the basis of the P-FMEA and the Process Flow Diagram . All control operations shall be numbered and correspond with P-FMEA and Process Flow Diagram. CC/SC shall be marked and identified. Dock Audit and Annual Layout. (Ref: VSM - SQPS-412; PPAP requirements). Veoneer may require additional controls - i.e. inspections that must be adhered to. First issue of Control plan shall be reviewed and updated to reflect actual level of risk identified during PPAP production Trial run including Interim Inspection Plan (SQPS-412). Questions to assist completeness: - Is a Production Control Plan per AIAG APQP&CP manual requirements included in this submittal? Any rework/repair operations shall be approved by Veoneer and included. - Are all sections filled out including evidence of cross functional team involvement? - Is the right part number and current index referred? - Is the original and version date noted? - Are Receiving Insp., Process Insp., Final Insp. included in CP? - Are CC/SC characteristics from DFMEA (if supplier is design responsible), PFMEA, and drawing included in CP? - Are performance testing requirements identified and are they at the proper intervals? - Is all manufacturing equipment identified i.e., press type, paint booth type, etc.? - Is the control method for CC/SC identified (e.g. X-bar & R chart)? - Is the date for the annual component layout defined? (If agreed in contract) - Are all inspection gages, techniques, and equipment identified? - Are appropriate reaction plans included in the Control Plan? - Is the CP available in English? - Is dock audit included as a step in the process?
Customer Engineering Approval | End Customer Engineering approval (if applicable) | PPAP | 3 | 3 | The Supplier shall provide evidence that the component has been approved by end customer engineering.
Sample Production Parts | Send x PPAP parts to y at z. Upload delivery note and/or tracking number of sample shipment respectively promote task when done. (Details x, y and z to be defined by Veoneer.) | PPAP | 14 | 2 | The supplier shall provide evidence that the sample of production parts have been or will be delivered according to delivery schedule. A Delivery Note or other relvant information shall be stored in that task. Production product sample = 300 pcs. or amount determined by Veoneer. Send X PPAP parts to Y at Z. Upload the delivery note and/or tracking number of sample shipment then respectively promote task when done. (Details X, Y and Z to be defined by Veoneer.)
Master Sample | 1. Master Sample packing list and tracking number (if applicable) Only ship if required by Facility SQE and 2. Upload photograph of Master Sample w/tag retained at supplier's facility. | PPAP | 15 | 3 | The supplier shall provide evidence that Master sample have been produced and are now retained at supplier. Pictures of these master samples shall be sufficient with their identification number. - If requested by SQE, is one (1) Master Sample identified and included in this PPAP submittal? - Is there an identified Master Sample from each manufacturing tool / process included?
Bulk Materials Requirements Checklist | Upload Bulk Materials Requirements Checklist (if applicable) | PPAP | 18 | 2 | The supplier shall provide evidence that the component is meeting requirements of Bulk Material. Get agreement with Veoneer for the bulk material requirements checklist if applicable. All requirements must be satisfied unless it is specified “no requirement” in the checklist.
PSW Submission | Upload the completed Part Submission Warrant (PSW) and, if applicable, agreed and Veoneer-signed Interim Recovery Worksheet (IRW). | PPAP | 18 | 1 | The supplier shall plan for preparation, submission and approval of PPAP documentation. In case submission date will be changed, supplier must inform Veoneer immediately using the S-APQP form. In case supplier will request an interim approval, the Interim Recovery Worksheet and any additional documents as defined by the using facility shall be submitted before PPAP. Reporting shall be done in accordance with the AIAG Production Part Approval Process manual (Ref. AIAG PPAP Manual and VSM - Quality Requirements - "PPAP") Questions to assist completeness: Is the PSW according to AIAG PPAP available? - Is the part name/number, engineering level, part classification, etc. of the warrant filled out correctly? - Is the "Supplier Manufacturing Information" & "Submission Information" correct? - Has the "Reason for Submission" been correctly identified? - Is the correct Submission Level identified? - Are the "Submission Results" filled out correctly and completely? - Is the "Declaration" filled out correctly and completely (including production rate)? - Are all parts required marked with the proper ISO re-cycle markings (plastics only)? - If submission is for Interim Approval is the IRW with Action Plan attached? - Is the PSW completed in English? - Is the part's shipping weight included to four (4) decimal places with the average of 10 pcs (x.xxxx kg)? - Is the PSW signed?
Key Milestone 3: Phase 3 | APQP Review confirmation. To be promoted by Veoneer SQ after review and release of all tasks related to this Milestone. | APQP |  | 2 | Milestone 3 aims at checking that all activities planned during Phase 3 are completed and that project can proceed. At this stage, when Milestone 3 is completed, the supplier will be able to deliver PPAP parts to the site that approved the components.
Run @ Rate | Upload Production Trial Run Report phase Run@Rate and the Production Trial Capacity Report (Ref. VSM Veoneer Production Trial Run Standard) | APQP |  | 3 | Date for Run at Rate shall be scheduled and included in S-APQP. Veoneer shall always be informed about time for realisation so the opportunity is given to attend. (Ref. VSM Product Life Cycle Step 7 "Production Trial Runs and 8 " PPAP and Run at Rate " and " Production Trial Run Standard "). The supplier shall evaluate after SOP and ramp up the actual capacity of their production line including total Quantity produced / Quantity rejected / Quantity OK parts.
Early Production Containment | Upload Completed IIP Appendix A Result Sheet. (Ref. VSM - SQPS-412) | APQP |  | 3 | The content of the enhanced control and inspection activities shall be defined, planned and agreed with Veoneer. Before termination of the actual activities, the supplier must get an approval from Veoneer. (Ref. SQPS-412 " Interim Inspection Plan "and VSM Product Life Cycle Step 10 "Performance Review / APQP Closure"). Supplier shall carry out a serial capability study to evaluate actual spread of characteristics versus pre-serial measurements. These data shall be used to evaluate opportunity to remove Interim Inspection plan.
Key Milestone 4: Phase 4 | APQP Review confirmation. To be promoted by Veoneer SQ after review and release of all tasks related to this Milestone. | APQP |  | 3 | Milestone 4 aims at checking that all activities planned during Phase 4 are completed and that the project can be closed.

## Information
Version # | Date | Author | Modification | Purpose
1 | 2020-01-22 | Dennis Nielsen | New Release