## Agenda
VESS 001 Appendix D - Calibration Agenda and Pre Work
VES Assessment Calibration Agenda
| VES Assessment Team: |  |  |  | Assessment Date: |  | 2018-11-09
| Purpose: | VES Calibration Visit |  |  | Site to be reviewed: |  | xxx
Date |  | Duration | Details | Responsible | Location | Comments
2018-11-02 |  | TBD | Review the calculation tab of the assessment and determine if all the needed information is available. If not then perfrom the necessary studies in advance of the assessment day 1. | Site VES Manager | TBD | Note: The order of the elements in the agenda can be adjusted to allow the right members of leadership to attend the right sections.
2018-11-09 |  |  | Assessment Calibration Day 1
8:00 | 8:30 | 0:30 | Introductions and Agenda Sharing | Calibration Leader | Meeting Room | Presentation of participants, Appendix C PPT + agenda
8:30 | 9:00 | 0:30 | Plant presentation | Local Plant Mgr | Meeting Room | General info about the plant
9:00 | 9:30 | 0:30 | To participate to the morning meeting (1 line support + plant level) | Team | Meeting Room | AMG + AMO (also good to visit AMC, but not necessary)
9:30 | 10:00 | 0:30 | Review and score all components of Team Work | Team | Meeting Room
10:00 | 10:15 | 0:15 | Break
10:15 | 11:45 | 1:30 | Validate Team Work scores on the Genba | Team | Genba
11:45 | 12:15 | 0:30 | Review and score all components of 5S | Team | Meeting Room
12:15 | 13:15 | 1:00 | Validate 5S scores on the Genba | Team | Genba
13:15 | 14:00 | 0:45 | Lunch
14:00 | 14:30 | 0:30 | Review and score all components of Standards | Team | Meeting Room
14:30 | 16:00 | 1:30 | Validate Standards scores on the Genba | Team | Genba
16:00 | 16:15 | 0:15 | Break
16:15 | 16:45 | 0:30 | Review and score all components of Muda Elimination | Team | Meeting Room
16:45 | 17:45 | 1:00 | Validate Muda Elimination scores on the Genba | Team | Genba
17:45 | 18:00 | 0:15 | Wrap up of Day 1 | VES + calibrators | Meeting Room
2018-11-10 |  |  | Assessment Calibration Day 2
8:00 | 9:00 | 1:00 | Review and score all components of TPM | Team | Meeting Room
9:00 | 10:00 | 1:00 | Validate TPM scores on the Genba | Team | Genba
10:00 | 10:15 | 0:15 | Break
10:15 | 11:15 | 1:00 | Review and score all components of JIT | Team | Meeting Room
11:15 | 13:15 | 2:00 | Validate JIT scores on the Genba | Team | Genba
13:15 | 14:00 | 0:45 | Lunch
14:00 | 14:45 | 0:45 | Review and score all components of Employee Involvement | Team | Meeting Room
14:45 | 15:45 | 1:00 | Validate Employee Involvement scores on the Genba | Team | Genba
15:45 | 16:00 | 0:15 | Break
16:00 | 16:45 | 0:45 | Review and score all components of Quality First | Team | Meeting Room
16:45 | 18:15 | 1:30 | Validate Quality First scores on the Genba | Team | Genba
18:15 | 18:30 | 0:15 | Wrap up of Day 2 | VES + calibrators | Meeting Room
2018-11-11 |  |  | Assessment Calibration Day 3
8:00 | 8:20 | 0:20 | Consolidation of element results, performance. | VES + calibrators | Meeting Room
8:20 | 9:05 | 0:45 | Summary and feedback to Plant Management + VES element teams | All | Meeting Room
9:05 | 11:05 | 2:00 | Define actions. 1:st step is to be creative, not to prioritize and select among ideas. Important to use the input directly after the calibration. | Local team | Meeting Room | Managed by local team. Calibrators available for support.
11:05 | 11:25 | 0:20 | Wrap Up | VES + calibrators | Meeting Room | Feedback about setup of calibration and agenda
|  |  | Select and prioritize among actions. 2:nd step. | Local team | Meeting Room | Can be done without calibrators at a later day.

## Preparations
VESS 001 Appendix D - Calibration Agenda and Pre Work
VES Assessment Calibration - Preparations
|  | Target date for the training | 2018-11-08 | Location | xxx
| # | Action | Responsible | Days before Training | Target Date | X=Complete | Comments
| 1 | Select dates for Calibration to occur together with the plant to be calibrated | Lead Calibrator | 90 | 2018-08-10
| 2 | Create agenda for the calibration days | Lead Calibrator | 45 | 2018-09-24 |  | Consider need of time for translation
| 3 | Select local participants to calibration event (from plant management team) | Local Plant | 30 | 2018-10-09 |  | Decide if translation is necessary
| 4 | Book a conference room with beamer for the calibration event | Local Plant | 30 | 2018-10-09
| 5 | Inform local organisation about calibration event | Local Plant | 30 | 2018-10-09
| 6 | Inform local organisation that the calibration team will join the plant morning meeting on day 1 | Local Plant | 7 | 2018-11-01
| 7 | Inform the Lead Calibrator of time to attend morning meeting in the plant | Local Plant | 7 | 2018-11-01
| 8 | Prepare KPI data | Local Plant | 7 | 2018-11-01
| 9 | Fill out data in the Calculations tab of the Assessment Excel file | Local Plant | 7 | 2018-11-01
| 10 | Print out organisation chart of the plant showing the different levels | Local Plant | 1 | 2018-11-07
| 11 | Print out the element tabs from the Assessment Excel file in A3 (one for each participant) | Local Plant | 1 | 2018-11-07
| 12 | Prepare write pads, one for each participant | Local Plant | 1 | 2018-11-07
| 13 |  |  |  | 2018-11-08
| 14 |  |  |  | 2018-11-08
| 15 |  |  |  | 2018-11-08
| 16 |  |  |  | 2018-11-08
| 17 |  |  |  | 2018-11-08
| 18 |  |  |  | 2018-11-08
| 19 |  |  |  | 2018-11-08
| 20 |  |  |  | 2018-11-08
| 21 |  |  |  | 2018-11-08
| 22 |  |  |  | 2018-11-08
| 23 |  |  |  | 2018-11-08
| 24 |  |  |  | 2018-11-08
| 25 |  |  |  | 2018-11-08
| 26 |  |  |  | 2018-11-08
| 27 |  |  |  | 2018-11-08
| 28 |  |  |  | 2018-11-08
| 29 |  |  |  | 2018-11-08
| 30 |  |  |  | 2018-11-08
| 31 |  |  |  | 2018-11-08
| 32 |  |  |  | 2018-11-08
| 33 |  |  |  | 2018-11-08
| 34 |  |  |  | 2018-11-08
| 35 |  |  |  | 2018-11-08
| 36 |  |  |  | 2018-11-08
| 37 |  |  |  | 2018-11-08
| 38 |  |  |  | 2018-11-08
| 39 |  |  |  | 2018-11-08
| 40 |  |  |  | 2018-11-08
| 41 |  |  |  | 2018-11-08
| 42 |  |  |  | 2018-11-08
| 43 |  |  |  | 2018-11-08
| 44 |  |  |  | 2018-11-08
| 45 |  |  |  | 2018-11-08
| 46 |  |  |  | 2018-11-08
| 47 |  |  |  | 2018-11-08
| 48 |  |  |  | 2018-11-08
| 49 |  |  |  | 2018-11-08
| 50 |  |  |  | 2018-11-08
| 51 |  |  |  | 2018-11-08
| 52 |  |  |  | 2018-11-08
| 53 |  |  |  | 2018-11-08
| 54 |  |  |  | 2018-11-08
| 55 |  |  |  | 2018-11-08
| 56 |  |  |  | 2018-11-08
| 57 |  |  |  | 2018-11-08
| 58 |  |  |  | 2018-11-08
| 59 |  |  |  | 2018-11-08
| 60 |  |  |  | 2018-11-08
| 61 |  |  |  | 2018-11-08
| 62 |  |  |  | 2018-11-08
| 63 |  |  |  | 2018-11-08
| 64 |  |  |  | 2018-11-08
| 65 |  |  |  | 2018-11-08
| 66 |  |  |  | 2018-11-08
| 67 |  |  |  | 2018-11-08
| 68 |  |  |  | 2018-11-08
| 69 |  |  |  | 2018-11-08
| 70 |  |  |  | 2018-11-08
| 71 |  |  |  | 2018-11-08
| 72 |  |  |  | 2018-11-08
| 73 |  |  |  | 2018-11-08
| 74 |  |  |  | 2018-11-08
| 75 |  |  |  | 2018-11-08
| 76 |  |  |  | 2018-11-08
| 77 |  |  |  | 2018-11-08
| 78 |  |  |  | 2018-11-08
| 79 |  |  |  | 2018-11-08
| 80 |  |  |  | 2018-11-08
| 81 |  |  |  | 2018-11-08
| 82 |  |  |  | 2018-11-08
| 83 |  |  |  | 2018-11-08
| 84 |  |  |  | 2018-11-08
| 85 |  |  |  | 2018-11-08
| 86 |  |  |  | 2018-11-08
| 87 |  |  |  | 2018-11-08
| 88 |  |  |  | 2018-11-08
| 89 |  |  |  | 2018-11-08
| 90 |  |  |  | 2018-11-08
| 91 |  |  |  | 2018-11-08
| 92 |  |  |  | 2018-11-08
| 93 |  |  |  | 2018-11-08
| 94 |  |  |  | 2018-11-08
| 95 |  |  |  | 2018-11-08
| 96 |  |  |  | 2018-11-08
| 97 |  |  |  | 2018-11-08
| 98 |  |  |  | 2018-11-08
| 99 |  |  |  | 2018-11-08
Formulas:
Target Date = D4-[Days before Training]